## Blad1
Planning project 1: Casa Parete |  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Casus: | Taak: | Omschrijving: | Naam:
Casus 1
| Taak 1 | Notulen | Felix | bar: Week 1 1
| Taak 2 | Algemene project geg. | I.V.Z. | bar: Week 1 1 to Week 3 1
| Taak 3 | Beganegrond | I.V.Z. | bar: Week 1 1 to Week 5 1
|  | Voorgevel | Hugo | bar: Week 1 1 to Week 5 1
|  | Achtergevel | Felix | bar: Week 1 1 to Week 5 1
|  | Doorsnede A-A | Rolf | bar: Week 1 1 to Week 5 1
|  | Doorsnede B-B | Ed | bar: Week 1 1 to Week 5 1
| Taak 4 | Maquette Casa Parete | Ed
|  | Perspectief | I.V.Z. | bar: Week 1 1 to Week 5 1
| Taak 5 | Koude bruggen | Team | bar: Week 1 1 to Week 3 1
| Taak 6 | Aanlegbreedte | Team | bar: Week 1 1 to Week 3 1
Casus 2
| Taak 1 | Notulen | Rolf | bar: Week 2 1
| Taak 2 | Verdieping | I.V.Z. | bar: Week 2 1 to Week 5 1
|  | Zolder | I.V.Z. | bar: Week 2 1 to Week 5 1
| Taak 3 | Maquette Casa Parete | Ed | bar: Week 2 1 to Week 5 7
|  | Perspectief | I.V.Z. | bar: Week 2 1 to Week 5 7
| Taak 4 | Detail 102b | bar: Week 2 1 to Week 5 1
|  | Detail 104q | Felix | bar: Week 2 1 to Week 5 1
|  | Detail 109b | Felix | bar: Week 2 1 to Week 5 1
Detail 332g | bar: Week 2 1 to Week 5 1
Detail 311c | bar: Week 2 1 to Week 5 1
| Taak 5 | Balkwapening | I.V.Z. | bar: Week 2 1 to Week 5 1
Casus 3
| Taak 1 | Notulen | Hugo | bar: Week 3 1
| Taak 2 | Fundering | I.V.Z. | bar: Week 3 1 to Week 5 1
|  | Situatie | I.V.Z. | bar: Week 3 1 to Week 5 7
| Taak 3 | Maquette Casa Parete | Ed | bar: Week 3 1 to Week 5 7
|  | Perspectief | I.V.Z. | bar: Week 3 1 to Week 5 7
| Taak 4 | Metselwerk | Hugo | bar: Week 3 1 to Week 5 1
|  | Schilderwerk | Rolf | bar: Week 3 1 to Week 5 1
|  | Dakbedekking | Ed | bar: Week 3 1 to Week 5 1
|  | Betonwerk | Felix | bar: Week 3 1 to Week 5 1
| Taak 5 | EP-waarde | Team | bar: Week 3 1 to Week 5 1
| Taak 6 | Vloerwapening | I.V.Z. | bar: Week 3 1 to Week 5 1
Casus 4
| Taak 1 | Notulen | Ed | bar: Week 4 1
| Taak 2 | Maquette Casa Parete | Ed | bar: Week 4 1 to Week 5 7
|  | Perspectief | I.V.Z. | bar: Week 4 1 to Week 5 7
| Taak 3 | Vervalt
| Taak 4 | Bouwaanvraag | I.V.Z. | bar: Week 4 1 to Week 5 1
| Taak 5 | Garagevloer | bar: Week 4 1 to Week 5 1
| Taak 6 | Gas | bar: Week 4 1 to Week 5 1
Water | bar: Week 4 1 to Week 5 1
Elektra | bar: Week 4 1 to Week 5 1
Riolering | bar: Week 4 1 to Week 5 1
Casus 5
| Taak 1 | Notulen | Felix | bar: Week 5 1
| Taak 2 | Voor. Presentatie | I.V.Z.
| Taak 3 | Rollenspel | Team
| Taak 4 | Presentatie | Team
Deze planning is gemaakt door F.Norambuena